Project Planning Phase: Project Planning Template

Date: 06 August 2026

Team ID:

Project Name: Automated Network Request Management

Platform / Domain: ServiceNow / IT Service Management (ITSM) / Network Operations

1. Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task Description | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup & Portal Intake | USN-1 | Establish Service Catalog taxonomy, create custom role matrices (sn_network_requester, sn_network_engineer), and design the baseline Requester Service Portal view with 8 categorized items. | 8 | High | Chinna Banisetti |
| Sprint-2 | Form Setup & Validation Logic | USN-2 | Build dynamic, intelligent catalog variable forms. Implement UI Policies to toggle conditional fields and Client Scripts with regex syntax rules for target IP address, subnet, and port checking. | 9 | High | Chinna Banisetti |
| Sprint-3 | Core Workflows & SLA Management | USN-3 | Configure multi-step approval paths via Flow Designer (Line Manager → Network Security team) and activate automated fulfillment task (sc_task) generation, SLA tracking clocks, and notification triggers. | 8 | Medium | Chinna Banisetti |
| Sprint-4 | End-to-End Testing & Deployment | USN-4 | Conduct end-to-end user scenario testing (UAT simulations, negative syntax tests, SLA breach validation), document project records, fix backlog bugs, and migrate Update Sets into production. | 5 | High | Chinna Banisetti |

2. Project Tracker & Agile Velocity

This tracker reflects your target milestone schedule leading up to your live project dates in June 2026.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 8 | 2 Days | 22 June 2026 | 23 June 2026 | 8 | 23 June 2026 |
| Sprint-2 | 9 | 2 Days | 24 June 2026 | 25 June 2026 | 9 | 25 June 2026 |
| Sprint-3 | 8 | 2 Days | 26 June 2026 | 27 June 2026 | 8 | 27 June 2026 |
| Sprint-4 | 5 | 1 Day | 28 June 2026 | 28 June 2026 | 5 | 28 June 2026 |

Velocity Metrics:

- Total Estimated Story Points: 30

- Total Development Window: 7 Days

Average Velocity=30 Story Points7 Days≈4.29 story points / day

3. Burndown Chart Data Structure

To plot your project burndown chart graphically within your presentation or report sheet, utilize the dataset below mapping the remaining work over your timeline:

| Timeline Timeline (End of Day) | Ideal Remaining Work (Story Points) | Actual Remaining Work (Story Points) | Status / Notes |
| --- | --- | --- | --- |
| Day 0 (Start) | 30 | 30 | Project Kickoff & Requirements Finalization |
| Day 1 (Mid Sprint-1) | 25.7 | 30 | Service Catalog layout structured in ServiceNow |
| Day 2 (End Sprint-1) | 21.4 | 22 | Sprint-1 Complete: Scoped setup & portal active (-8 SP) |
| Day 3 (Mid Sprint-2) | 17.1 | 22 | Form variables and client validation logic drafted |
| Day 4 (End Sprint-2) | 12.9 | 13 | Sprint-2 Complete: Dynamic validation scripts active (-9 SP) |
| Day 5 (Mid Sprint-3) | 8.6 | 13 | Flow Designer approval trees and routing maps built |
| Day 6 (End Sprint-3) | 4.3 | 5 | Sprint-3 Complete: SLA rules & Flow triggers complete (-8 SP) |
| Day 7 (End Sprint-4) | 0 | 0 | Sprint-4 Complete: UAT signed off, platform live (-5 SP) |

Burndown Visualization Guide: When drawing your line graph, plot the Timeline on the horizontal X-axis and the Remaining Story Points on the vertical Y-axis. Run the Ideal line straight from 0,30 down to 7,0, then plot your Actual line along the points tracking your actual remaining numbers (30, 30, 22, 22, 13, 13, 5, 0).